## Home
NSW Water Efficiency Framework rating tool
The NSW Water Efficiency Framework is a best-practice guide to developing and delivering water efficiency. It provides clear steps to design, deliver and review water efficiency programs. Government, water utilities, councils and large businesses will find guidance on implementing water efficiency initiatives no matter what their level of maturity. This rating tool can be used as a workbook to track and self-rate progress towards best practice.
Using the framework tool:
Each of the elements and enabling factors can be found in the tabs along the bottom of the workbook. Start at establish context and work across the tabs. On each sheet you will enter a rating, justification and recommended actions.
You can self rate the criteria qualitatively on a 5-point scale based on these descriptors.
The structure of the framework:
|  | Phases | There are 3 overarching phases: plan, implement and review.
|  | Elements | There are 5 elements: establish context, analyse situation, develop response, design and deliver options and monitor, report and adapt. Each element has a number of steps that contributes to its success.
|  | Steps | Each element consists of 2-3 steps.
|  | Enabling factors | Each element is supported by 3 enabling factors: identify and engage with stakeholders, secure resourcing and ensure governance, capture and share knowledge.
|  | Criteria | For each of the elements in the framework, we have developed evaluation criteria to help identify progress towards water efficiency best practice.
|  | Performance | Dynamic bar charts indicate progress towards best practice for each element and enabling factor. You can view overall progress on the Framework tab.
|  | Justification | Record justification for the rating.
|  | Recommended actions | Record recommended actions to make improvements.
|  | Guiding questions | There are a series of guiding questions that give practical prompts to guide what needs to happen for each element and enabling factor.
The NSW Water Efficiency Framework rating tool was developed for DPE by the Institute for Sustainable Futures (University of Technology Sydney)
2022-11-01
ISF2022

## Establish context
Establish context
| Steps | Evaluative criteria | Rating (drop down) | Justification | Recommended actions | Guidance
10 | Understand strategic context | The drivers for water efficiency are clearly identified. | Not done |  |  | Why is the program being developed? Drivers: What are the drivers for water efficiency (e.g., need to better prepare for drought, address supply/ demand imbalance, support resilient, prosperous and livable cities and towns, meet regulatory requirement) Strategic alignment: What broader internal and external strategies, plans and policies support a water efficiency program (e.g., carbon neutral plan, sustainability goals, community strategic plan, supply-demand planning strategy)?
|  | Internal guiding strategies and plans are identified and the linkages to water efficiency are clear. | Good practice
10 |  | External links to broader NSW government objectives are clear. | Good practice
11 | Set objectives | The water efficiency goals are broad and represent both immediate needs and a long-term vision including relevant input from stakeholders and/or community. | Good practice |  |  | What will the program achieve? Goals, objectives and outcomes: What are the water efficiency goals, objectives and outcomes? Is a target appropriate? If so, what? If not, what else will drive efficiency investment?
11 |  | The objectives and outcomes are realistic, specific and can be evaluated. | Not applicable
12 | Define boundaries | The scope of the water efficiency program is clear. |  |  |  | Who, what and where the water efficiency program covers? Scope: What is the scope of the program (e.g., all water saving opportunities on either side of the meter, from water source to water use, all potable water uses or losses, also non-potable water use/loss, all customers types or utility/ council water use and losses only)? Geographical boundary: What is the geographical boundary of the program (e.g., state, city or town, supply system, suburb)? Timeframe: What time period does the water efficiency program cover (e.g., 5yrs, 15yrs or 30yrs) Does the timeframe align with the broader strategies identified above? Process: What steps of the water efficiency framework will you undertake at this time and why? What will you not to do this time?
12 |  | The geographical boundaries are defined.
12 |  | The period for the water efficiency program aligns with strategic drivers (e.g., strategy, plans and regulation).
Each step of the framework is considered. The steps, responsible parties and resources required are clear. There is clear justification for omitting any steps from the framework.
a1 | Identify & engage with community & stakeholders | Stakeholders and the community are identified and a stakeholder engagement plan is developed. Stakeholders are appropriately engaged throughout the process. |  |  | Recommneded actions can be entered on the enabling factor tab: Community & stakeholders. | Stakeholders: Who are the key stakeholders (consider government departments, utilities, local councils, other divisions within utility, community, customers, industry groups)? Who within your organisation is responsible for engaging them? How and when during the process will they be engaged? How are water users that are not direct customers engaged? Has the case for water efficiency been made to internal stakeholders and decision makers and risks, benefits and costs explained? Community expectations: What are community/stakeholder values/expectations for water efficiency? How will they benefit? What are their drivers for water efficiency?
Stakeholder and community expectations for water efficiency are understood.
a1 |  | Internal stakeholders and decision makers support water efficiency and understand the risks, costs and benefits.
b1 | Secure resourcing & ensure governance | A clear governance structure gives oversight with balanced representation and authority, ensuring process is conducted robustly, outcomes are achieved and funding is allocated and used. |  |  | Recommneded actions can be entered on the enabling factor tab: Resourcing & governance | Governance: Who is responsible for water efficiency within your organisation? How will a range of views and diversity in background be included in decisions? Are there clear lines of authority, reporting requirements and resourcing? Is there clear oversight of the funding? How is funding allocated and reviewed? Funding: Are funding mechanisms established, are they adequate to support all aspects of water efficiency? Who has access to funding? Does the funding timeframe align with overall program? Resourcing: What resources will you need to undertake the water efficiency program? Is it clear who is responsible for each step? If there are multiple responsible parties, is it clear who has the lead? Are there adequate resources (people time and money) allocated for each step? Who is responsible for ensuring that each step is adequately funded and resourced? Is there a diverse steering group for the process that has appropriate expertise and knowledge?
b1 |  | Resources are available to deliver all appropriate elements of the framework - not just options delivery. This includes funding, capacity & capability.
b1 |  | Roles and responsibilities are clear.
b1 |  | Technical steering group is established that can provide appropriate expertise and knowledge.
c1 | Capture & share knowledge | Knowledge is captured, securely stored and shared to build internal and broader industry capacity and capability. |  |  | Recommneded actions can be entered on the enabling factor tab: Knowledge sharing | Knowledge capture & dissemination: How can your organisation’s and the water industry’s capacity and capability be built? What data and information will be captured from the program? How and where will information be captured and stored? How long for? Are there any privacy issues with the capture/ storage/ sharing of information that need to be addressed? Who will be responsible for building and maintaining the knowledge repository from this and future programs? Water literacy: How can literacy be fostered? What information would allow customers to be more aware of water use? What are the key elements of water efficiency that need to be understood?
c1 |  | Key elements of water efficiency are communicated in an appropriate form to all sectors of the community.
c1 |  | The community is engaged in water efficiency and understands their contribution.

## Analyse situation
Analyse situation
| Steps | Evaluative criteria | Rating (drop down) | Justification | Recommended actions | Guidance
21 | Identify risks and opportunities | Risks and opportunities assessment undertaken. |  |  |  | What could limit and support water efficiency outcomes ? Metering and Monitoring: Is demand measured (metering/ end-use)? Can data be easily extracted and broken down into appropriate segments? Data driven decision making: Is there enough information and resources to do analysis at the level required? E.g., is the system well understood (supply/demand balance, water quality, ecosystem, costs structures and, future constraints and limitations)? Are customer and stakeholder preferences understood? Is the information available for different time scales (now, future) and spatial scales (any differences across the service area). Impacts of water efficiency: What are the financial and economic implications of water efficiency across all sectors? Does the customer pricing regime encourage or hinder water efficiency? Have you considered the opportunity for hardship programs to be a driver? Lessons learnt: What can you learn from past experience (past programs, other jurisdictions, R&D, pilots)?
21 |  | Metering and end use data is accessible.
21 |  | Data requirements and gaps are identified.
22 | Undertake demand analysis | There is an agreed baseline for current demand and growth |  |  |  | How and where is water used? Baseline demand: When do you begin measuring savings. How will you consider the impacts of seasonal and annual weather variability (wet vs dry years), population growth or loss of large users? Disaggregation: Do you have data for all customers (including utility demand, losses from dams and distribution)? Can the data be segmented by customer type and/or disaggregated by end uses (toilet/ taps) and end users (residential, hospital) ? Do you have data for all water sources (potable and non-potable systems)? Savings opportunities: What value does water efficiency have? How does the water demand compare to supply availability, system capacity, other similar areas, benchmarks? What are the opportunities by customer type, by end use?
22 |  | Demand data has been analysed and disaggregated to understand water use and target water savings opportunities.
a2 | Identify & engage with community & stakeholders | An appropriately diverse and knowledgeable group of stakeholders and community representatives are included in the risk and opportunity identification. |  |  | Recommneded actions can be entered on the enabling factor tab: Community & stakeholders. | Is a diverse group from across the organisation included in the assessment of risks and opportunities (community, strategic planners, demand forecasters, operations, comms, IT, regulatory, customer service, government stakeholders)?
a2 |  | Customer segmentation has been used to identify, refine and target programs and messaging.
b2 | Secure resourcing & ensure governance | Sufficient capacity and capability is available to interrogate data and to model current and future demand (disaggregated). |  |  | Recommneded actions can be entered on the enabling factor tab: Resourcing & governance | Are there enough resources - including funding, capacity and capability - for the necessary level of analysis? Is it possible to analyse data when neede
c3 | Capture & share knowledge | Information is available for program analysis including potential savings, costs, lessons learnt, end use data and stock information. |  |  | Recommneded actions can be entered on the enabling factor tab: Knowledge sharing | Is there information on end uses, appliance and fixture stock surveys for the local area, or can information from elsewhere be adapted?

## Develop response
Develop response
| Steps | Evaluative criteria | Rating (drop down) | Justification | Recommended actions | Guidance
31 | Identify options | Past options are reviewed for new opportunities. |  |  |  | What options are available? Learning from the past: What options have been tried in the past? What worked well, what could be improved, what opportunities remain? What opportunities have not been adopted? Why? What would need to change to make the option useful? What is happening in other jurisdictions, what could be adopted or tested? Emerging options: What has been learnt from pilots or R&D? What new options and technologies have emerged? What technologies have become more effective/efficient since the last scan? Addressing risks and opportunities: What options can address each segment of demand, address specific end uses, specifically “low-hanging fruit”? What are customer preferences, What options could address identified risks or opportunities? Coverage: What end uses and end users are covered by options? What delivery models are available for options (rebate, service provision)?
31 |  | Regular scans of options in other jurisd.ictions & emerging opportunities are undertaken.
31 |  | Pilots and R&D are done to identify new options for your context.
31 |  | Current programs gather data to identify further options and opportunities.
32 | Design & assess options | Maps the long list of options to end use, end user, goals, objectives, risks and opportunities to develop a short list of viable options and R&D / pilot needs. |  |  |  | How do the options compare individually? What design alternatives are available for options, and how do they align with the intended program outcomes? Coverage of potential options: What is the long list of options (from above) and how do they map with goals, objectives, full range of end users, end-uses, risks and opportunities (e.g., foundational capacity, ability to ramp up, ability to collect data for future programs, engage customers, support market transformation)? Data: What data is available to base assessments of cost and water savings for options? How robust are the cost and savings estimates? How could you fill knowledge gaps? Are further R&D / pilots required? What is the longevity of savings - do they grow or decay over time? Feasibility: How easy are the options to implement? How acceptable are the options to customers? Are there other implementation mechanisms? How do they compare? Economic evaluation: What assessment framework will you use (cost benefit analysis, cost effectiveness analysis using levelised cost)? What are your comparison baselines, do they vary in time or spatially? Does the option have additional benefits such as social equity, liveability, energy reduction, wastewater reduction, ease of implementation etc.? What is the distribution of the costs and benefits (between customers and the utility)?
32 |  | Ranks viable options using a consistent and robust economic assessment framework (from a whole of society perspective).
32 |  | Considers trade-offs and other consistent criteria beyond costs and savings
| Develop & evaluate options packages | Packages of options are evaluated for overall savings, overall cost and other objectives as appropriate. |  |  |  | What group of options best meets program goals and objectives? Scale of saving: Will the scale of water savings from your proposed options package meet your strategic goals? Coverage and overlap: How can viable options be combined to avoid overlap? How does the program meet different objectives (e.g., delays supply augmentation or provides drought readiness or mitigates the impacts of restrictions or provides foundational capacity, community engagement, relationship building)? How well does the package of options cover the range of end-uses and end users? How well does the total package address risks and opportunities? Does it make sense to do slightly more expensive options that have better water savings and lower risks (e.g., retrofits over showerhead swap)?
Package of options has broad coverage (all customers, whole system, education, relationship building, capacity building etc).
a3 | Identify & engage with community & stakeholders | Diverse groups are included in identifying options. |  |  | Recommneded actions can be entered on the enabling factor tab: Community & stakeholders. | What stakeholders and community groups are involved in options identification (e.g., industry experts and associations, government)? What representatives from across the business are involved (e.g., comms, education, operations, customer service)? What stakeholders and community groups are involved in options design (e.g., coms, education, operations, industry experts)?
a3 |  | Targeted stakeholder and community engagement has been done when designing the relevant options.
b3 | Secure resourcing & ensure governance | Package of options approved. |  |  | Recommneded actions can be entered on the enabling factor tab: Resourcing & governance | Governance: Has the package of options been approved to go to detailed design of options? Resourcing: Is there capacity and capability to identify and assess the full range of options? What gaps are there? How will you fill them? Funding: Is the funding adequate & secure to deliver all of the options in the final package? Is separate funding available to cover R&D? Has collaborative funding been explored?
b3 |  | Sufficient capacity and capability to identify and assess options.
b3 |  | Enough funding (includign collaborative funding) has been secured to design, deliver, evaluated and report on all options, including R&D.
c3 | Capture & share knowledge | Options are designed to generate and capture knowledge on the individual option and the effect on customer water demand. |  |  | Recommneded actions can be entered on the enabling factor tab: Knowledge sharing | Is information available on past options? Is information on emerging options available? Where/ how will you get the data to assess the options (costs, water savings, feasibility)?

## Design and deliver options
Design and deliver options
| Steps | Evaluative criteria | Rating (drop down) | Justification | Recommended actions | Guidance
41 | Undertake pilots and R&D | Pilots or R&D are designed to fill data gaps and test customer response, and include an evaluation process. |  |  |  | How can pilots and R&D be used to fill gaps and develop more robust water efficiency options? Viability of new options: What are the emerging technologies or approaches that could be tested? Who can you collaborate with? What emerging methods could be tested or adopted from other sectors? What do you need to know to decide if an option is worth pursuing further? Feasibility testing of viable options (Pilots): What are the data gaps? What do you need to know before rolling out the option at scale? What are the implementation issues – technical, delivery mechanisms? Are there different delivery mechanisms that need testing? Are there different products you could offer (e.g., basic and premium products).
42 | Detailed design of options | A detailed implementation plan for each option is developed, including how and when to expand/ extend/ exit, how to collect, storage and use data for evaluation and reporting. |  |  |  | How will each option be delivered? Detailed design: Who are you targeting? Who do you need to involve in the planning/ rollout? What is the scale of the program? How will you know when the option has reached saturation? How long will the option run for? How will it be wrapped up? Can it be extended or expanded? Evaluation information: What criteria will the options be evaluated against (including costs and savings, uptake, customer feedback)? What is the baseline? How long before the program can be evaluated? How will you evaluate it and how often? What data do you need to evaluate? How will this feed into the option reporting and review process? What approvals do you need to use and share the data (e.g. customer approval to use their data to evaluate savings). Reporting: How will information be shared and to whom?
42 |  | A robust evaluation methodology is developed for each option, including clear baseline.
| Implement options | Delivery team's roles and responsibilities are clear. |  |  |  | How will you manage implementation? Delivery: Are you meeting your milestones? How is the budget tracking? Is the product/service meeting quality requirements? How is the uptake/acceptance trending? How are you tracking and escalating risks? How are you reporting on the project to your governance group? Is proactive communications and media reaching target audiences? How are you responding to reactive communications and media? Real time review: Are you capturing the information you need to review the project? Adaptation: How are you addressing stakeholder feedback? How are you refining your delivery based off your performance metrics? How are you adapting your program to make sure it’s still achieving planned objectives, outcomes and benefits?
Processes are in place to capture lessons learned and consider them.
Option is tracked and evaluated in real time against anticipated outcomes and adapted as needed.
a4 | Identify & engage with community & stakeholders | Stakeholder and community input has been sought for detailed options & pilots design. |  |  | Recommneded actions can be entered on the enabling factor tab: Community & stakeholders. | Detailed options design: What stakeholders do you need to engage in the detailed options design (e.g., community groups, business groups, education, operations, industry experts)? Have opportunities for program collaboration across boundaries been explored? Pilot and R&D: What stakeholders do you need to engage in the detailed options design (e.g., coms, education, operations, industry experts)? Communications: What is the communications strategy for maximizing the value of the strategy? How are water users that are not direct customers engaged?
a4 |  | Communication plan has been developed for water efficiency options and program.
a4 |  | Process are in place to explore collaboration and partnership opportunities for R&D, pilots and options delivery, and/or programs across boundaries.
b4 | Secure resourcing & ensure governance | Detailed delivery of options/ R&D endorsed including implementation, review, expansion, end of options. |  |  | Recommneded actions can be entered on the enabling factor tab: Resourcing & governance | Governance: Has approval been sought to implement the option / program? Have success / review criteria been agreed for options and pilots/ R&D? Resourcing: What skills do you need to deliver the program overall? What skills do you need to deliver each particular option (e.g., IT, coms, billing, project delivery, data analytics)? What is your delivery method? What resources do you have available? What is missing and how can you fill the gaps? What training (capacity building) is required? Funding: What will each program cost (project management, contract management, procurement, evaluation and review, piloting, comms and marketing etc.)? How will it be funded, what happens if uptake is greater/ less than expected for costs and funding?
b4 |  | Multi-disciplinary team is established with the capacity and capability to deliver the full program, with clearly assigned roles and responsibilities.
b4 |  | Enough fundingis secured to design, deliver, evaluated and report on all options, including R&D/ pilots.
c4 | Capture & share knowledge | Option and program implementation insights are documented and shared. |  |  | Recommneded actions can be entered on the enabling factor tab: Knowledge sharing | Implementation: How will options insights (water savings, uptake, stock data) and program implementation insights (issues with equipment, buy-in, reaching customers, sampling/ evaluation) be documented and shared? Pilot and R&D: What are the outcomes of the pilots? How can they be adapted for broader roll out?

## Monitor, report, adapt
Monitor, report, adapt
| Steps | Evaluative criteria | Rating (drop down) | Justification | Recommended actions | Guidance
51 | Evaluate program | Robust evaluations are completed for all options using rapid / interim data collection where possible. |  |  |  | How have the options and program overall met their intended outcomes? Options evaluation: How have individual options performed (e.g., costs, savings, uptake, feedback)? Is the option meeting expected outcomes? What were the gaps? What were the key lessons learnt? Program evaluation: How has the program as a whole performed (e.g., costs, savings, feedback, meeting goals and objectives)? What were the gaps? What were the key lessons learnt? Process evaluation: Was the governance adequate? Were roles and responsibilities clear? Were there sufficient resources and capability? What could be done differently next time? Were any new risks or opportunities identified?
51 |  | Program as a whole has been evaluated and reassessed in relation to objectives.
51 |  | Gap analysis on options, program and process is completed.
52 | Report | Regular reports provide information on all water efficiency initiatives undertaken in the reporting period, covering costs, savings, lessons learnt, other benefits. |  |  |  | How and what will you report? Reporting: How will you report? What will you report (e.g., costs, savings, lessons learnt, other benefits)? Who will you report to? How often will you report?
52 |  | Options and program performance is compared against expected outcomes, including implications for IWP.
52 |  | A program for the future is identified.
53 | Adapt | Individual options and program overall and process are adapted using lessons learnt. |  |  |  | What lessons have been learnt? What needs to change? Adapting from options & program lessons learnt: What has been learnt? What options should be continued/ expanded/ discontinued/ modified? Adapting to changed context: What has changed? Are the objectives and drivers still relevant? Are they driving the right outcomes? Refining the program: Are there new options that should be added/ considered? What new R&D/pilots are required? What additional capacity/capability is required? What else is needed to support the program?
a5 | Identify & engage with community & stakeholders | Stakeholders and community groups are included in review process as appropriate. |  |  | Recommneded actions can be entered on the enabling factor tab: Community & stakeholders. | Which stakeholders and community groups should you include in the the program review, to gain reflections on programs (e.g., experience and improvement opportunities)? With whom will you share lessons learnt? How effective was the stakeholder engagement during the process? What could be done differently next time?
a5 |  | Stakeholder and community engagement comsiders proposed program refinement and lessons learnt.
b5 | Secure resourcing & ensure governance | Program reporting, proposed adaptations and forward program are all endorsed. |  |  | Recommneded actions can be entered on the enabling factor tab: Resourcing & governance | Governance: Have reporting, adaptations and forward program been approved? Resourcing: Is there capacity and capability to appropriately evaluate the program as a whole and individual options? How was the program delivered overall? What resourcing or funding gaps were there? What is required to improve capability?
b5 |  | The efficacy of resourcing and funding to achieve overall program objectives, accounting for lessons learnt, has been reviewed.
b5 |  | Capacity and capability to do evaluation for options, program and process.
| Capture & share knowledge | Information is kept up to date and easily accessible. |  |  | Recommneded actions can be entered on the enabling factor tab: Knowledge sharing | Knowledge capture & dissemination: What have you learnt, how can it be shared, with whom? What would you like to know in the future? How can that be built into the future program? Have you shared your evaluated project or program savings and cost effectiveness via publications or conferences?
c5 |  | Knowledge and experiences have been shared with the water industry.

## Community & stakeholders
Identify & engage with community & stakeholders
| Steps | Evaluative criteria (carried over) | Rating (carried over) | Justification (carried over) | Recommended actions
a1 | Plan | Stakeholders and the community are identified and a stakeholder engagement plan is developed. Stakeholders are appropriately engaged throughout the process.
Stakeholder and community expectations for water efficiency are understood.
a1 |  | Internal stakeholders and decision makers support water efficiency and understand the risks, costs and benefits.
a2 |  | An appropriately diverse and knowledgeable group of stakeholders and community representatives are included in the risk and opportunity identification.
a2 |  | Customer segmentation has been used to identify, refine and target programs and messaging.
a3 |  | Diverse groups are included in identifying options.
a3 |  | Targeted stakeholder and community engagement has been done when designing the relevant options.
a4 | Implement | Stakeholder and community input has been sought for detailed options & pilots design.
a4 |  | Communication plan has been developed for water efficiency options and program.
a4 |  | Process are in place to explore collaboration and partnership opportunities for R&D, pilots and options delivery, and/or programs across boundaries.
a5 | Review | Stakeholders and community groups are included in review process as appropriate.
a5 |  | Stakeholder and community engagement comsiders proposed program refinement and lessons learnt.

## Resourcing & governance
Secure resourcing & ensure governance
| Steps | Evaluative criteria (carried over) | Rating (carried over) | Justification (carried over) | Recommended actions
b1 | Plan | A clear governance structure gives oversight with balanced representation and authority, ensuring process is conducted robustly, outcomes are achieved and funding is allocated and used.
b1 |  | Resources are available to deliver all appropriate elements of the framework - not just options delivery. This includes funding, capacity & capability.
b1 |  | Roles and responsibilities are clear.
b1 |  | Technical steering group is established that can provide appropriate expertise and knowledge.
b2 |  | Sufficient capacity and capability is available to interrogate data and to model current and future demand (disaggregated).
b3 |  | Package of options approved.
b3 |  | Sufficient capacity and capability to identify and assess options.
b3 |  | Enough funding (includign collaborative funding) has been secured to design, deliver, evaluated and report on all options, including R&D.
b4 | Implement | Detailed delivery of options/ R&D endorsed including implementation, review, expansion, end of options.
b4 |  | Multi-disciplinary team is established with the capacity and capability to deliver the full program, with clearly assigned roles and responsibilities.
b4 |  | Enough fundingis secured to design, deliver, evaluated and report on all options, including R&D/ pilots.
b5 | Review | Program reporting, proposed adaptations and forward program are all endorsed.
b5 |  | The efficacy of resourcing and funding to achieve overall program objectives, accounting for lessons learnt, has been reviewed.
b5 |  | Capacity and capability to do evaluation for options, program and process.

## Knowledge sharing
Capture & share knowledge
| Steps | Evaluative criteria (carried over) | Rating (carried over) | Justification (carried over) | Recommended actions
c1 | Plan | Knowledge is captured, securely stored and shared to build internal and broader industry capacity and capability.
c1 |  | Key elements of water efficiency are communicated in an appropriate form to all sectors of the community.
c1 |  | The community is engaged in water efficiency and understands their contribution.
c2 |  | Information is available for program analysis including potential savings, costs, lessons learnt, end use data and stock information.
c3 |  | Options are designed to generate and capture knowledge on the individual option and the effect on customer water demand.
c4 | Implement | Option and program implementation insights are documented and shared.
| Review | Information is kept up to date and easily accessible.
c5 |  | Knowledge and experiences have been shared with the water industry.

## RawResults (hidden)
[9 empty] | 25% | 50% | 75% | 100% | 0%
Code | Section | Step | Criteria | Band | Score | Total | Possible | % | Red | Orange | Yellow | Green | None | Bar chart
10 | Establish context | Understand Strategic Context | The drivers for water efficiency are clearly identified. | Not done | 1 | 7 | 12 | 58.33% | FALSE | FALSE | 58.33% | FALSE | 41.67%
| Establish context | Understand Strategic Context | Internal guiding strategies and plans are identified and the linkages to water efficiency are clear. | Good practice | 3
10 | Establish context | Understand Strategic Context | External links to broader NSW government objectives are clear. | Good practice | 3
11 | Establish context | Set Objectives | The water efficiency goals are broad and represent both immediate needs and a long-term vision including relevant input from stakeholders and/or community. | Good practice | 3 | 3 | 4 | 75% | FALSE | FALSE | FALSE | 75% | 25%
11 | Establish context | Set Objectives | The objectives and outcomes are realistic, specific and can be evaluated. | Not applicable | 0
12 | Establish context | Define Boundaries | The scope of the water efficiency program is clear. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
12 | Establish context | Define Boundaries | The geographical boundaries are defined. | 0 | 0
12 | Establish context | Define Boundaries | The period for the water efficiency program aligns with strategic drivers (e.g., strategy, plans and regulation). | 0 | 0
12 | Establish context | Define Boundaries | Each step of the framework is considered. The steps, responsible parties and resources required are clear. There is clear justification for omitting any steps from the framework. | 0 | 0
21 | Analyse Situation | Identify Risks and Opportunities | Risks and opportunities assessment undertaken. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
21 | Analyse Situation | Identify Risks and Opportunities | Metering and end use data is accessible. | 0 | 0
21 | Analyse Situation | Identify Risks and Opportunities | Data requirements and gaps are identified. | 0 | 0
22 | Analyse Situation | Undertake Demand Analysis | There is an agreed baseline for current demand and growth | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
22 | Analyse Situation | Undertake Demand Analysis | Demand data has been analysed and disaggregated to understand water use and target water savings opportunities. | 0 | 0
31 | Design Response | Identify Options | Past options are reviewed for new opportunities. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
31 | Design Response | Identify Options | Regular scans of options in other jurisd.ictions & emerging opportunities are undertaken. | 0 | 0
31 | Design Response | Identify Options | Pilots and R&D are done to identify new options for your context. | 0 | 0
31 | Design Response | Identify Options | Current programs gather data to identify further options and opportunities. | 0 | 0
32 | Design Response | Design & Assess Options | Maps the long list of options to end use, end user, goals, objectives, risks and opportunities to develop a short list of viable options and R&D / pilot needs. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
32 | Design Response | Design & Assess Options | Ranks viable options using a consistent and robust economic assessment framework (from a whole of society perspective). | 0 | 0
32 | Design Response | Design & Assess Options | Considers trade-offs and other consistent criteria beyond costs and savings | 0 | 0
33 | Design Response | Develop & Evaluate Options Packages | Packages of options are evaluated for overall savings, overall cost and other objectives as appropriate. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
33 | Design Response | Develop & Evaluate Options Packages | Package of options has broad coverage (all customers, whole system, education, relationship building, capacity building etc). | 0 | 0
41 | Implement | Undertake Pilots and R&D | Pilots or R&D are designed to fill data gaps and test customer response, and include an evaluation process. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
42 | Implement | Detailed Design of Options | A detailed implementation plan for each option is developed, including how and when to expand/ extend/ exit, how to collect, storage and use data for evaluation and reporting. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
42 | Implement | Detailed Design of Options | A robust evaluation methodology is developed for each option, including clear baseline. | 0 | 0
| Implement | Implement Options | Delivery team's roles and responsibilities are clear. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
| Implement | Implement Options | Processes are in place to capture lessons learned and consider them. | 0 | 0
| Implement | Implement Options | Option is tracked and evaluated in real time against anticipated outcomes and adapted as needed. | 0 | 0
51 | Monitor, Report, Adapt | Evaluate Program | Robust evaluations are completed for all options using rapid / interim data collection where possible. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
51 | Monitor, Report, Adapt | Evaluate Program | Program as a whole has been evaluated and reassessed in relation to objectives. | 0 | 0
51 | Monitor, Report, Adapt | Evaluate Program | Gap analysis on options, program and process is completed. | 0 | 0
52 | Monitor, Report, Adapt | Report | Regular reports provide information on all water efficiency initiatives undertaken in the reporting period, covering costs, savings, lessons learnt, other benefits. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
52 | Monitor, Report, Adapt | Report | Options and program performance is compared against expected outcomes, including implications for IWP. | 0 | 0
52 | Monitor, Report, Adapt | Report | A program for the future is identified. | 0 | 0
53 | Monitor, Report, Adapt | Adapt | Individual options and program overall and process are adapted using lessons learnt. | 0 | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
a1 | Identify & engage with community & stakeholders | Establish Context | Stakeholders and the community are identified and a stakeholder engagement plan is developed. Stakeholders are appropriately engaged throughout the process. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
| Identify & engage with community & stakeholders | Establish Context | Stakeholder and community expectations for water efficiency are understood. |  | 0
a1 | Identify & engage with community & stakeholders | Establish Context | Internal stakeholders and decision makers support water efficiency and understand the risks, costs and benefits. |  | 0
a2 | Identify & engage with community & stakeholders | Analyse Situation | An appropriately diverse and knowledgeable group of stakeholders and community representatives are included in the risk and opportunity identification. |  | 0
a2 | Identify & engage with community & stakeholders | Analyse Situation | Customer segmentation has been used to identify, refine and target programs and messaging. |  | 0
a3 | Identify & engage with community & stakeholders | Design Response | Diverse groups are included in identifying options. |  | 0
a3 | Identify & engage with community & stakeholders | Design Response | Targeted stakeholder and community engagement has been done when designing the relevant options. |  | 0
a4 | Identify & engage with community & stakeholders | Implement Options Program | Stakeholder and community input has been sought for detailed options & pilots design. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
a4 | Identify & engage with community & stakeholders | Implement Options Program | Communication plan has been developed for water efficiency options and program. |  | 0
a4 | Identify & engage with community & stakeholders | Implement Options Program | Process are in place to explore collaboration and partnership opportunities for R&D, pilots and options delivery, and/or programs across boundaries. |  | 0
a5 | Identify & engage with community & stakeholders | Monitor, Report, Adapt | Stakeholders and community groups are included in review process as appropriate. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
a5 | Identify & engage with community & stakeholders | Monitor, Report, Adapt | Stakeholder and community engagement comsiders proposed program refinement and lessons learnt. |  | 0
b1 | Secure resourcing & ensure governance | Establish Context | A clear governance structure gives oversight with balanced representation and authority, ensuring process is conducted robustly, outcomes are achieved and funding is allocated and used. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
b1 | Secure resourcing & ensure governance | Establish Context | Resources are available to deliver all appropriate elements of the framework - not just options delivery. This includes funding, capacity & capability. |  | 0
b1 | Secure resourcing & ensure governance | Establish Context | Roles and responsibilities are clear. |  | 0
b1 | Secure resourcing & ensure governance | Establish Context | Technical steering group is established that can provide appropriate expertise and knowledge. |  | 0
b2 | Secure resourcing & ensure governance | Analyse Situation | Sufficient capacity and capability is available to interrogate data and to model current and future demand (disaggregated). |  | 0
b3 | Secure resourcing & ensure governance | Design Response | Package of options approved. |  | 0
b3 | Secure resourcing & ensure governance | Design Response | Sufficient capacity and capability to identify and assess options. |  | 0
b3 | Secure resourcing & ensure governance | Design Response | Enough funding (includign collaborative funding) has been secured to design, deliver, evaluated and report on all options, including R&D. |  | 0
b4 | Secure resourcing & ensure governance | Implement Options Program | Detailed delivery of options/ R&D endorsed including implementation, review, expansion, end of options. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
b4 | Secure resourcing & ensure governance | Implement Options Program | Multi-disciplinary team is established with the capacity and capability to deliver the full program, with clearly assigned roles and responsibilities. |  | 0
b4 | Secure resourcing & ensure governance | Implement Options Program | Enough fundingis secured to design, deliver, evaluated and report on all options, including R&D/ pilots. |  | 0
b5 | Secure resourcing & ensure governance | Monitor, Report, Adapt | Program reporting, proposed adaptations and forward program are all endorsed. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
b5 | Secure resourcing & ensure governance | Monitor, Report, Adapt | The efficacy of resourcing and funding to achieve overall program objectives, accounting for lessons learnt, has been reviewed. |  | 0
b5 | Secure resourcing & ensure governance | Monitor, Report, Adapt | Capacity and capability to do evaluation for options, program and process. |  | 0
c1 | Capture & share knowledge | Establish Context | Knowledge is captured, securely stored and shared to build internal and broader industry capacity and capability. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
c1 | Capture & share knowledge | Establish Context | Key elements of water efficiency are communicated in an appropriate form to all sectors of the community. |  | 0
c1 | Capture & share knowledge | Establish Context | The community is engaged in water efficiency and understands their contribution. |  | 0
c2 | Capture & share knowledge | Analyse Situation | Information is available for program analysis including potential savings, costs, lessons learnt, end use data and stock information. |  | 0
c3 | Capture & share knowledge | Develop Response | Options are designed to generate and capture knowledge on the individual option and the effect on customer water demand. |  | 0
c4 | Capture & share knowledge | Implement Options Program | Option and program implementation insights are documented and shared. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
c5 | Capture & share knowledge | Monitor, Report, Adapt | Information is kept up to date and easily accessible. |  | 0 | 0 | 0 |  | FALSE | FALSE | FALSE | FALSE | 100%
| Capture & share knowledge | Monitor, Report, Adapt | Knowledge and experiences have been shared with the water industry. |  | 0

## Raw Calcs (hidden)
Lower | Points | Upper | Rating Criteria
3.5 | 4 | 4 |  | Best practice | Undoubtable meets, or exceeds, requirements.
2.5 | 3 | 3.5 |  | Good practice | Satisfies requirements, or only a minor level of implementation required to satisfy requirements
1.5 | 2 | 2.5 |  | Emerging practice | Far from meeting requirement. Still in consideration phase. Extensive work required to meet requirements.
0.5 | 1 | 1.5 |  | Not done | Element not currently addressed.
- | 0 | - |  | Not applicable | Element not required for particular context